## Instructions
Pilot Project Tracker
InnoLead Innovation Toolkit
Purpose
Give every pilot the same spine: a one-line objective, explicit success criteria, a budget, and a recorded scale-or-stop decision — so pilots end in a decision rather than drifting.
How to use this workbook
| 1. | Adjust statuses, outcomes, business units and risk levels on the Lists tab.
| 2. | Add one row per pilot on the Pilots tab. Write the objective and success criteria before the pilot starts.
| 3. | Update Spend to date monthly; budget used % and duration calculate themselves.
| 4. | At pilot close, set Criteria met? and Decision. A Scale decision shades green, Stop shades red.
| 5. | Pair each completed pilot with the Technology Pilot Postmortem template to capture lessons learned.
What is in each tab
| Tab | What it does
| Instructions | This page — purpose, workflow and colour key.
| Pilots | The pilot register. One row per pilot, 40 rows pre-formatted.
| Summary | Counts and budget by status and business unit, plus charts.
| Lists | Statuses, outcomes, business units and risk levels.
Colour key and notes
| Blue text | You type here (assumptions and data entry)
| Black text | Formula — do not overwrite
| Green text | Pulled from another tab in this workbook
| • | A pilot without written success criteria cannot be judged — fill column G before the start date.
| • | Budget used % over 100% shades red so overspending pilots surface immediately.
| • | Cancelled and Stop outcomes are healthy signals; a portfolio with none is not testing hard enough.

## Lists
Reference Lists
Edit these values to fit your organisation — dropdowns update automatically
Pilot Status | Outcome | Business Unit | Risk | Success Met
Planned | Pending | Corporate | Low | Pending
In flight | Scale | Operations | Medium | Yes
Paused | Extend | Commercial | High | Partially
Complete | Stop | Digital |  | No
Cancelled | Inconclusive | R&D
Supply Chain

## Pilots
Pilot Project Tracker
Track pilot objectives, milestones, budget and outcomes through to a scale-or-stop decision
ID | Pilot name | Partner / vendor | Business unit | Pilot owner | Objective (one line) | Success criteria | Start date | End date | Status | Risk | Budget ($) | Spend to date ($) | Budget used % | Duration (days) | Criteria met? | Decision | Next step
| Vision QA line 3 | Northlight Vision | Operations | P. Ibrahim | Cut false-reject rate on line 3 | False rejects down 30% | 2026-03-02 | 2026-08-28 | In flight | Medium | 85000 | 41000 |  |  | Pending | Pending | Mid-pilot review 14 July
| Warehouse autonomous pick | Corvus Robotics | Supply Chain | A. Dubois | Test pick throughput uplift | Picks/hour up 20% | 2026-01-12 | 2026-05-30 | Complete | Low | 95000 | 92000 |  |  | Yes | Scale | Business case to Q3 gate
| Smart metering retrofit | GridSense | Corporate | R. Chen | Validate energy savings at 3 sites | Energy use down 8% | 2025-10-06 | 2026-02-27 | Complete | Low | 60000 | 58000 |  |  | Partially | Extend | Extend to 6 more sites
| Contract review assistant | Internal | Corporate | J. Silva | Reduce contract turnaround time | Turnaround under 5 days | 2026-04-13 | 2026-09-30 | In flight | High | 70000 | 24000 |  |  | Pending | Pending | Data protection review
| Recycled pallet loop | Berg Logistics | Supply Chain | K. Berg | Prove closed-loop pallet economics | Cost per trip down 12% | 2026-02-16 | 2026-06-30 | Paused | High | 45000 | 19000 |  |  | Pending | Pending | Awaiting supplier capacity
TOTAL

## Summary
Pilot Summary
Every figure below is calculated from the Pilots tab
Headline metrics
| PILOTS LOGGED |  |  | IN FLIGHT |  | TOTAL PILOT BUDGET
| SPEND TO DATE |  |  | DECISIONS TO SCALE |  | HIGH-RISK PILOTS
Pilots by status
| Pilot Status | Count | Budget ($) |  | Business Unit | Count | Budget ($)